CA-FedDef Research Execution Roadmap

4-Week Sprint to First Paper  |  March 24 – April 19, 2026

Mentor: Ola (Oluseyi Olaolu Olukola)  |  Student: PhD Mentee  |  Target: IEEE TIFS submission (first-draft milestone by Week 4)

# Mission

Produce a complete, reproducible experimental result set for the CA-FedDef framework — specifically the NIMA attack demonstration and the dual-threshold detection response — sufficient to draft the core paper sections within 4 weeks. This is the deliverable that matters to Professor Rahimi. Everything else is secondary.

| Week 1 Mar 24–29 | Week 2 Mar 30–Apr 5 | Week 3 Apr 6–12 | Week 4 Apr 13–19 |
| --- | --- | --- | --- |

| Env + Baselines | Attack Injection + NIMA | CA-FedDef Implementation | Results + Paper Draft |
| --- | --- | --- | --- |
| Exit: Clean F1 table (3 baselines, IID + non-IID) | Exit: NIMA ASR table proving baselines fail (>50%) | Exit: CA-FedDef vs NIMA — ASR drops below 20% | Exit: Results tables + §1–4 paper draft submitted to Ola |

# GitHub Repository

The repo is already scaffolded with all folders, base classes, and placeholder files. The student's job is to implement — not to design the structure.

| Item | Detail |
| --- | --- |
| Repo name | ca-feddef-research |
| Visibility | Private — mentor + student only |
| Branch strategy | main (stable) + dev (student work) — student NEVER pushes to main directly |
| Weekly PR deadline | Every Friday 5pm — student opens PR from dev to main. No PR = week not complete. |
| Commit standard | Minimum 1 meaningful commit per working day. Empty days are flagged in check-in. |

Boilerplate repo structure (pre-scaffolded by mentor):

ca-feddef/

├── README.md  (setup instructions + week targets)

├── requirements.txt

├── config/default_config.yaml

├── data/  (download scripts + preprocess.py + partition.py)

├── federated/  (server.py + client.py)

├── federated/aggregation/  (fedavg.py, krum.py, fltrust.py)

├── federated/ca_feddef/  (cpb.py, ats.py, pga.py, llaf.py)

├── attacks/  (smp.py, lfa.py, nima.py)

├── experiments/  (e1_baseline.py … e4_ablation.py)

├── results/  (.gitkeep)

└── utils/  (metrics.py, logging.py)

# Week 1  |  March 24–29  |  Environment + Baselines

| Goal | Exit Criterion | If Missed |
| --- | --- | --- |
| FL simulation running on CICIoT2023 with 3 baselines under IID + non-IID conditions | A results table: Macro-F1 for FedAvg, Krum, FLTrust × {IID, α=0.3, α=0.1} | No Week 2 start. Student explains blockers on Monday standup, mentor co-debugs. |

| Day | Task | Owner | Exit Gate / Deliverable | Status |
| --- | --- | --- | --- | --- |
| Mon Mar 24 | Clone repo. Install requirements. Verify environment (Python, Flower, scikit-learn, numpy). Run smoke test script. | Student | smoke_test.py passes with no errors (13+ checks). Environment confirmed before any data work. | TODO |
| Mon Mar 24 | Download CICIoT2023 dataset. Verify file integrity. Document download path in README. Run preprocess.py (--n_files 10) immediately after download. Confirm data/processed/ directory is populated before moving to partition. | Student | data/processed/X_train.npy and y_train.npy exist. class_stats.csv shows 8 classes. preprocess.py ran without errors. | TODO |
| Tue Mar 25 | Implement data/partition.py: Dirichlet Dir(α) partitioning into N=10 simulated clients. α ∈ {IID, 0.3, 0.1}. | Student | label_dist_alpha0.3.png saved and verified. Heatmap shows uneven colour = non-IID working. Per-client X_client_N.npy files present in results/partitions/. | TODO |
| Tue Mar 25 | Implement resource tier assignment: 20% Tier A, 50% Tier B, 30% Tier C. Store in config. | Student | Client tier mapping printed and saved to results/tier_assignment.json | TODO |
| Wed Mar 26 | Implement federated/server.py + client.py. Scaffold FL training loop using Flower. FedAvg aggregation only. | Student | 10-round training completes without crash. Loss curve saved. | TODO |
| Wed Mar 26 | 10-minute check-in with Ola. Review partition plots + FL loop output. Unblock any issues. | Ola + Student | Check-in completed. Issues logged in GitHub Issues. | TODO |
| Thu Mar 27 | Implement federated/aggregation/krum.py and fltrust.py. Integrate with server. | Student | Both aggregators run to completion with same FL loop. | TODO |
| Fri Mar 28 | Run Experiment E1: all 3 baselines (FedAvg, Krum, FLTrust) × {IID, α=0.3, α=0.1} × 100 rounds. Record Macro-F1, Accuracy. | Student | results/e1_baseline_clean.csv populated. Table exported. | TODO |
| Fri Mar 28 | Open PR from dev to main with week 1 work. Write PR description summarising what was done. | Student | PR open by 5pm Friday. Ola reviews by Sunday. | TODO |
| Sat–Sun | Ola reviews PR. Approves or requests fixes. Student addresses review comments before Monday. | Ola | PR merged or clear list of fixes for Monday. | TODO |

Week 1 non-negotiable output:

Preprocessed data verified (data/processed/ populated, class_stats.csv reviewed) AND a CSV + readable table showing clean Macro-F1 for 3 methods across 3 data conditions. If both exist, Week 1 is complete. The preprocessing is non-negotiable — a model trained on raw unprocessed data will produce invalid results regardless of what the metrics show.